## Test Cases
Project Name | Fabric Lagbe |  | TC Start Date | 26/12/2021 | TC Execution Start Date | 13/9/2022 |  | TEST CASE SUMMARY
Module Name | Registration, Sign In |  | TC End Date | 29/12/2021 | TC Execution End Date | 15/9/2022 |  | PASS | 26
Epic |  |  | Test Case Developed By | Dilruba Khanam Jesey | Browser (tested) | Yes |  | FAIL | 25
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  | NOT EXECUTED | 0
[8 empty] | OUT OF SCOPE | 0
Test Executed by | [7 empty] | TOTAL | 51
Test Case ID/Name | Module | Feature | Test Case Description | Test Steps | Test Data | Expected Result | Actual result | Status | Bug Screenshots
TC001 | User Management | Registration | Enter a valid email & password | Step1-Go to https://fabriclagbe.com/register Step-2 Enter valid email Step-3 Enter valid password Step-4 Click on submit button | Email: Jess.jesey@gmail.com Password: Jerry111111@ | Register Successful | Register Successful | PASS
TC002 |  |  | Enter a valid email & invalid password | Step1-Go to https://fabriclagbe.com/register Step-2 Enter valid email Step-3 Enter invalid password Step-4 Click on submit button | Email: Jess.jesey@gmail.com Password: 1234 | A popup message box to show an error "Invalid email or password" | Bring back to registration form again for fillout the form again. Don't show any "Invalid email or password" error after submitting the form. | FAIL
TC003 |  |  | Enter an invalid email & valid password | Step1-Go to https://fabriclagbe.com/register Step-2 Enter invalid email Step-3 Enter valid password Step-4 Click on submit button | Email: abcd@1234 Password: Jerry111111@ | A popup message box to show an error "Invalid email or password" | Bring back to registration form again for fillout the form again. Don't show any "Invalid email or password" error after submitting the form. | FAIL
TC004 |  |  | Enter an invalid email & invalid password | Step1-Go to https://fabriclagbe.com/register Step-2 Enter invalid email Step-3 Enter invalid password Step-4 Click on submit button | Email: abcd@1234 Password: 1234 | A popup message box to show an error "Invalid email or password" | Bring back to registration form again for fillout the form again. Don't show any "Invalid email or password"error after submitting the form. | FAIL
TC005 |  |  | Enter invalid phone number | Step1-Go to https://fabriclagbe.com/register Step-2 Enter invalid Phone number Step-3 Click on submit button | Phone number: 12344567888 | A popup message box to show an error "Invalid phone number" | Show the message successful registration. After submitting the form show "Phone verification" and ask for "enter your code". | FAIL
TC006 |  |  | Enter random Png in NID field | Step1-Go to https://fabriclagbe.com/register Step-2 Submit wrong NID Png Step-3 Click on submit button | Screenshot (579).png | A message should be shown as this is not a NID PNG | No error message is given. Complete the registration successfully. | FAIL
TC007 |  |  | Keep empty all the required field | Step1-Go to https://fabriclagbe.com/register Step-2 Enter Name Step-3: Enter Phone Number Step-4: Click on submit button | Full Name: Dilruba khanam jesey Phone number: 01645329898 | Error message should be given in the empty field as "Field is required to be complete" | No error message is given in the empty field. Refresh the registration form again for fillout the form again without given an error message. | FAIL
TC008 |  |  | Test Seller/Employer Button | Step1-Go to https://fabriclagbe.com/register Step-2 Fill all the field in the registration form Step-3: Fill Seller/Employ button with wrong information Step-4: Click on submit button | Full Name: Dilruba khanam jesey Phone number: 01866181399 Email: Jess.jesey@gmail.com Password: Jerry111111@ Company Name: ssdfg Your Designation: hhgfsa Company Address: asssssssssssss | Should give an error message " Company Info is not correct". Please fill with correct information. | Register Successful. | FAIL
TC009 |  |  | Verify Job Info Form | Step1: Go thttps://fabriclagbe.com/register Step-2: Click on register Step-3: Fill all the field in the registration form Step-4: Fill Job button all information Step-5: In the job info UI, Colon is missing Step-6: Click on submit button | "Division ':' " "District ':' " "Duration for joining to new job ':' " "Industry sub category ':' " "Industry employee type ':' " "Years of experience in above expertise ':' " | Should give an error message | Register Successful. | FAIL
TC010 |  |  | Verify Boundary value : Max+1 | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-2 Fill all the field in the registration form Step-3: Fill 48 character in Password field as max vale is 47 Step-4: Click on submit button | 1.1111e+53 | Should give an error message like upper limit exceed. | Password doesn't match with confirm password. | FAIL | TC_16
TC011 |  |  | Verify Boundary value : Min-1 | Step1:Go thttps://fabriclagbe.com/register Step 2: Click on register Step 3 Fill all the field in the registration form Step 4: Fill 7 character in Password field as min value is 8 Step-5: Click on submit button | Jay111$ | Register Successful | Only refresh the page. Don't give an error message. | FAIL | TC_17
TC012 |  |  | Verify Max value 47 | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Fill all the field in the registration form Step-4: Fill 47 character in Password field as max value is 47 Step-5: Click on submit button | Jay121212$11111111111111111111111111111111111111 | Register Successful | Password doesn't match with confirm password. | FAIL | TC_18
TC013 |  |  | Use color on Buyer/Seller/Job button $ Bold them | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3: Fill all the field in the registration form Step-4: Fill the info of Buyer/seller/employee button Step-5: Click on submit button | Full Name: Dilruba khanam jesey Phone number: 01866181399 Email: Jess.jesey@gmail.com Password: Jerry111111@ Company Name: ssdfg Your Designation: hhgfsa Company Address: asssssssssssss | Register Successful | Only refresh the page. Don't show any error. | FAIL | TC_19
TC014 |  |  | Check Already Have an Account is clickable or not | 1. Go to https://fabriclagbe.com/register 2.click on the already have an account option 3. Check if it's clickable nor not 4.Click on submit button | N/A | Link isn't clickable. | Link isn't clickable. | PASS | TC_20
TC015 |  |  | Verify Login Now option is clickable | 1. Go to https://fabriclagbe.com/register 2.Click on the Login Now option 3. Check if it's clickable nor not 4.Click on submit button | N/A | Link is clickable and will take in Login Form. | Link is clickable and it has take in Login Form. | PASS | TC_21
TC016 |  |  | Verify user Log in interface is Okay or Not | 1. Go to https://fabriclagbe.com/register 2. Check all the fields and button are Okay or Not. 3. Click on Submit Button | N/A | User log in interface is okay | User log in interface is okay | PASS
TC017 |  |  | Verify with empty field of phone number and password | 1. Go to https://fabriclagbe.com/register 2. Keep number & password field empty. 3. Click on submit button. | N/A | Error message will be shown. | Phone number already exist message shown. | PASS
TC018 |  |  | Check email text box validation | 1. Go to https://fabriclagbe.com/register 2. Click on register 3.fill field with invalid email. 4. Check validation | abc@123.com | show a validation error message | there is no validation error message | FAIL | Email text box validation
TC019 |  |  | Verify if all the field is empty | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Keep empty all the field Step-4: Click on submit button | N/A | A error message should given like please fill all the field. | No error message is shown. | FAIL | Verify if all the field is empty
TC020 |  |  | Check all the text boxes, radio buttons, buttons & alligned properly. | 1. Go to https://fabriclagbe.com/register 2. Click on register 3. Check text boxes,Radio buttons, buttons all are properly aligned. | N/A | All the text boxes and buttons working and properly aligned | Height of the select your Product willing to sell field are not same to the other field | FAIL | Text boxes, radio buttons, buttons & alligned properly
TC021 |  |  | Verify by not filling Company Info required field | 1. Go to https://fabriclagbe.com/register 2. Click on register 3. Keep empty Company Info required field. | N/A | An error message should given. Required field should be filled. | No error message is shown. Only reload the page. | FAIL | Not filling Company Info required field
TC022 |  |  | Check in Job Info all fields are alligned & worked propoerly. | 1. Go to https://fabriclagbe.com/register 2. Click on register 3. Click on Job Button 4. Check all the boxes & allignment. | N/A | All the text boxes & allignment is okay. | All the text boxes & allignment is okay. | PASS
TC023 |  |  | Verify by using same phone number. | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Fill all the field Step-Step-4: Fill same phone number Step-5: Click on submit button | Phone: 1964644395 | Register Successful. | This phone number already exist error message shown. | FAIL | Using same phone number
TC024 |  |  | Verify Password with one special character, at least one uppercase and have a numerical. | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Fill all the field in the registration form Step-4: Fill password with one special character, at least one uppercase and have a numerical. Step-5: Click on submit button | Pass: Rai222222@ | Register Successful. | Ask for verification code and then register successfully. | PASS | Password with one special character, at least one uppercase and a numerical
TC025 |  |  | Verify password should be encrypted and shown in an asterisk(****) | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Fill all the field in the registration form Step-4: Enter Password & should be in asterisk Step-5: Click on submit button | *************** | Register Successful. | Register Successful. | PASS
TC026 |  |  | Verify whether the validation added for the password and confirm password whether pass is same or not. | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Fill password filled. Step-4: Fill confirm pass with wrong value. Step-5: Click on submit button | Pass: Rai22222$ Confirm pass: ssssdd12& | Register Successful. | Register Successful. | PASS
TC027 |  |  | Verify an eye icon added to the password and confirm password field. | Step-1: Click on register Step-2: Check eye icon on password field whether it's working | N/A | Register Successful. | Register Successful. | PASS
TC028 |  |  | Verify example data shown as placeholder text in the fields. | Step-1: Click on register Step-2: Check placeholder field has been added for example data field. | N/A | Placeholder text has added for example field. | Placeholder text hasn't been added for example field. | FAIL
TC029 |  |  | Verify that the user can access the different controls by pressing 'Tab' key on the keyboard. | Step-1: Click on register Step-2: Check all the field by using Tab. | N/A | User can access by pressing 'Tab' key on the keyboard. | User can access by pressing 'Tab' key on the keyboard. | PASS | https://www.loom.com/share/44cd3a0a92714cbc99dffb4f54868978
TC030 |  |  | Test by trying to register with an already registered email address. | Step1-Go to https://fabriclagbe.com/register Step-2: Click on register Step-3 Fil all the field. Step-4: Fill email field with an used email. Step-5: Click on submit button. | Jess.jesey@gmail.com | Can't register. Will show an error message. | Show an register successful message. Asked for phone verification code. | FAIL | https://www.loom.com/share/d3f6d3dd762d41cc9e0ec161fdd2890a
TC031 |  |  | Verify the email verification link was sent to the user's email address successfully. | Step-1: Click on register Step-2: Check by enter an valid email if verification link was sent. | Jess.jesey@gmail.com | Verification link will be sent. | No verification link hasn't been send. | FAIL
TC032 |  |  | Verify that user should not able to access in website until user verifies by clicking on the link sent in the email. | Step-1: Click on register Step-2: Check by enter an valid email if verification link was sent. | Jess.jesey@gmail.com | Verification link will be sent and can't access without it. | Email Verification link hasn't sent. Verify by phone verification code. | FAIL
TC033 |  |  | Verify resend OTP code is present if the user did not receive the code in first. | 1. Click on register. 2. Fill the form with valid number & fill all the field with valid info. 3. Submit the form. Check if the OTP has been send or not. If not resend it. | OTP: 12345 | OTP will resend. | OTP has resend. | PASS
TC034 |  |  | Verify captcha is added to form or not. | 1. Click on register. 2. Check Captcha is available or not. | N/A | Available | Not available. | FAIL
TC035 |  |  | Verify grammatical or spelling mistake | 1. Click on register. 2. Check spelling mistake in full register page. | N/A | All spelling is okay. | All spelling is okay. | PASS
TC001 |  | Sign In | Verify that labels and controls including text-boxes, buttons and links are present on the login page. | Step-1 Go to https://fabriclagbe.com/ Step-2 Click on Sign In button. Step-3. Check text-boxes, buttons and links are present.. | N/A | All are available | All are available | PASS
TC002 |  |  | Verify Forget Password is working properly | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. Click on Forget Password 4. Check it's working or not | N/A | Clickable | Clickable | PASS | https://www.loom.com/share/81c36553fa5a45bb8ea69c8c68ca12bd
TC003 |  |  | Verify Need an Account is working | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. Click on Need an Account option 4. Check it's working or not 5. Check whether it's taken on registration page | N/A | Working | Not Working | FAIL | https://www.loom.com/share/81c36553fa5a45bb8ea69c8c68ca12bd
TC004 |  |  | Verify Register Now Option is working | 1. Go to https://fabriclagbe.com/login 2. Click on Register Now option 3. Check it's working or not | N/A | Working | Working & it's take on Registration page | PASS | https://www.loom.com/share/81c36553fa5a45bb8ea69c8c68ca12bd
TC005 |  |  | Check validation of all the fields | 1. Go to https://fabriclagbe.com/ 2 Fill Phone number field with valid value 3. Fill Password field with invalid value 4. Check validation | 01964644396 gfdsafff | Validation has been Done. | Validation is working for Phone Number. Password don't have validation. | FAIL | https://www.loom.com/share/f9224f21c7e04453afa340ef512c9ed5
TC006 |  |  | Verify if the length of the phone number is incorrect i.e. greater than 11. | Step-1-Go to https://fabriclagbe.com/ Step-2: Click on sign in button Step-3 Fil the phone number field greater than 11 digit. Step-4: Click on login button. | 1964644395678 | Should show an validation error message $ login will be failed. | Show validation error. Give an error message-> These credentials do not match with our records. | PASS | Login_Phone Greater than 11 digit
TC007 |  |  | Verify if the length of the phone number is incorrect i.e. greater than 11 & keep empty the other field. | Step-1-Go to https://fabriclagbe.com/ Step-2: Click on sign in button Step-3 Fil the phone number field greater than 11 digit. Step-4: Keep other field empty. Step-5: Click on login button. | 19646443956784 | Should show an validation error message and login should failed. | Show an validation error message->In password field give an message fill out this field->login hasn't taken. | PASS | Login_Phone greater than 11_Keep empty other field
TC008 |  |  | Verify if all the field is empty. | 1. Go to the url 2. Go to https://fabriclagbe.com/ 3. Click on Sign In button. 4. don’t fill any field of login page 5. click login button | N/A | Please fill out phone and password field then sign up-> an error message should given. | No error message shown. When click in Login button it takes on password field for fill up. | FAIL | Login_Keep empty all the field
TC009 |  |  | Verify with Invalid phone no and valid password | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3.Enter invalid Phone no 4.Enter valid password 5. Click on login button | Phone: 01112222222222222222222 Pass: Rai1111111$ | Should give an error message. | Show validation error in phone field. Give an error message-> These credentials do not match with our records. | PASS | Login_Invalid phone & valid pass
TC010 |  |  | Verify with valid phone no and invalid password | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3.Enter valid Phone no 4.Enter invalid password 5. Click on login button | Phone: 01626980347 Pass: ssddfas | Should show valid in phone field. give an error message-> These credentials do not match with our records. | Should show valid in phone field. give an error message-> These credentials do not match with our records. | PASS | Login_valid phone & invalid pass
TC011 |  |  | Verify with valid phone no and password | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3.Enter valid Phone no 4.Enter valid password 5. Click on login button | Phone: 01964644395 Pass: Rai111111@ | Should show an valid message in phone field and Login successfully. | Show an valid message in phone field. After login successfully it takes Buyer dashboard page. | PASS | Login_Valid phone & pass
TC012 |  |  | Verify grammatical or spelling mistake | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. A new page will appear having Sign In button. 4. Check whether any grammatical or spelling mistake | N/A | No grammatical or spelling mistake | Don't have any grammatical or spelling mistake | PASS
TC013 |  |  | Verifying whether Sign In page appears | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. A new page will appear having Sign In button. | N/A | A Sign In UI should apear | A Sign In UI have appeared | PASS
TC014 |  |  | Checking password field is masked | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. A new page will appear having Sign In button. 4. Fill the field in password | Pass: sdfgh12% | Written password should be masked | Written password is in masked. | PASS
TC015 |  |  | Clicking Eye icon on password field | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. A new page will appear having Sign In button. 4. Fill the field in password 5. Click on Eye icon | Pass: sdfgh12% | Written password should be visible | Written password is visible | PASS
TC016 |  |  | Verify Login Button is working | 1. Go to https://fabriclagbe.com/ 2. Click on Sign In button. 3. A new page will appear having Sign In button 4. Fill the field or keep empty 5. Click on Login Button | N/A | If field will fill with valid value,after clicking in login button login successful message will show. If fill with invalid value, error message will be shown. | After fill with valid value, clicking on login button login has successfully done. After fill with invalid value, error message show like-> these credentials do not match with our records. | PASS

## Test Case Summary
Test Case Summary
Project Name - | Fabric Lagbe
Module Name - | User management Module |  |  |  |  | Total No. | Status | Result :
Test Case Version | 1.0.0 |  |  |  |  | 26 | PASS
Written By | Dilruba Khanam Jesey |  |  |  |  | 25 | FAIL
Executed By | Dilruba Khanam Jesey |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | [5 empty] | 0 | Out of Scope |  |  | Test Environment
TEST EXECUTION SUMMARY
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 26 | 25 | 0 | 0 | 51
Grand Total | 26 | 25 | 0 | 0 | 51
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
SNO | Required Data |  | Value
1 | No. of requirements
2 | Avg. No. of Test Cases written per requirements
3 | Total No. of Test Cases written for all requirements |  | 51
4 | Total No. of Test Cases executed |  | 51
5 | No. of Test Cases passed |  | 26
6 | No. of Test Cases failed |  | 25
7 | No. of Test Cases blocked
8 | No. of Test Cases unexecuted |  | 0
9 | Total No. of defects identified
10 | Critical defects count
11 | Higher defects count
12 | Medium defects count
13 | Low defects count
14 | Customer defects
15 | No. of Defects found in UAT
Test Metrics Calculation
|  | Covered Area |  | Formula | Parcentage(%)
|  | Executed Test Cases |  | (No of ex TC/Total number of TC written)*100 | 100
|  | Not Executed Test Cases |  | (No of not ex TC/Total number of TC written)*100 | 0
|  | Passed Test Cases |  | (No of TC passed/Total number of TC executed)*100 | 50.9804
|  | Failed Test Cases |  | (No of TC failed/Total number of TC executed)*100 | 49.0196
|  | Blocked Test Cases |  | (No of TC blocked/Total number of TC executed)*100
|  | Defect Density |  | (No of Defect found/Size(Number of requirements))*100
|  | Defect Leakage |  | (No of Defect found in UAT/Number of defect fount in test)*100
|  | Defect Rejection |  | (No of Defect rejected/Number of defect raised)*100
|  | DRE (Defect Removal Efficiency) |  | (A/A+B)*100 where, A= defect indentified/Fixed defect B= Defect identified by customer/ Missed defect
|  | Defect Age |  | Fixed Date- Repoted date

## Bug Report
Bug Reporting
TC-018
Issue: | Check email text box validation
Test Steps: | 1. Go to https://fabriclagbe.com/register 2. Click on register 3.fill field with invalid email. 4. Check validation
Env: | Testing
Module: | User Management
Severity: | P4
Screenshot: | Email text validation
Responsible QA: | Jesey